# RMMM Plan (Risk Mitigation, Monitoring, and Management)

## Project: NL2SQL System

# Step 1: Forming a Risk Table

A risk table provides a simple technique for risk projection. The risks are listed below:

| RISK ID | RISKS | CATEGORY | PROBABILITY | IMPACT | RMMM |
| --- | --- | --- | --- | --- | --- |
| 1 | Inaccurate SQL query generation for complex user inputs | TE | 60% | 2 | Implement multi-shot prompting, human-in-the-loop validation, and fallback mechanisms |
| 2 | System vulnerabilities like prompt injection causing unauthorized DB access | PS | 40% | 1 | Apply strict input sanitization, least-privilege DB access, and query validation before execution |
| 3 | High latency in generating SQL affecting user experience | TE | 50% | 3 | Optimize API calls, implement caching for frequent queries, and use smaller/faster models where possible |
| 4 | Inability to handle domain-specific jargon or ambiguous queries | CU | 70% | 2 | Integrate a domain-specific dictionary, add query clarification prompts for the user |
| 5 | Database schema changes breaking the NL2SQL mapping | PD | 30% | 2 | Automate schema synchronization, maintain versioned schema metadata, and add regression tests |

# Step 2: Sort the risks in descending order based on probability

| RISK ID | RISKS | CATEGORY | PROBABILITY | IMPACT | RMMM |
| --- | --- | --- | --- | --- | --- |
| 4 | Inability to handle domain-specific jargon or ambiguous queries | CU | 70% | 2 | Integrate a domain-specific dictionary, add query clarification prompts for the user |
| 1 | Inaccurate SQL query generation for complex user inputs | TE | 60% | 2 | Implement multi-shot prompting, human-in-the-loop validation, and fallback mechanisms |
| 3 | High latency in generating SQL affecting user experience | TE | 50% | 3 | Optimize API calls, implement caching for frequent queries, and use smaller/faster models where possible |
| 2 | System vulnerabilities like prompt injection causing unauthorized DB access | PS | 40% | 1 | Apply strict input sanitization, least-privilege DB access, and query validation before execution |
| 5 | Database schema changes breaking the NL2SQL mapping | PD | 30% | 2 | Automate schema synchronization, maintain versioned schema metadata, and add regression tests |

# Step 3: Risk Information Sheet (RIS) for each Risk

## Risk Information Sheet (RIS) for 70% Risk

Risk ID: 4	Date: 24/04/2026	Probability: 70%	Impact: 2

| Description | Inability to handle domain-specific jargon or ambiguous queries, leading to incorrect or failed SQL generation. |
| --- | --- |
| Refinement & Context | Sub condition 1: Users input highly specialized terminology not present in the LLM training data. Sub condition 2: Queries are inherently ambiguous or lack sufficient context. Sub condition 3: Missing database schema descriptions confuse the model. |
| Mitigation & Monitoring Strategies | 1. Integrate a domain-specific glossary and schema descriptions. 2. Implement a feedback loop to ask users for clarification. 3. Log failed queries to expand training data. 4. Fine-tune the model with domain-specific examples. |
| Contingency Plan and Management | 1. Provide a default fallback response. 2. Fallback to basic keyword-based search. 3. Flag query for manual review. 4. Route to a human expert if available. |
| Trigger | High rate of syntax errors in generated SQL or repeated user query modifications. |
| Status | Mitigation actions planned (Vocabulary building in progress) |
| Assigned To | AI/ML Engineer |
| Originator | Development Team |

## Risk Information Sheet (RIS) for 60% Risk

Risk ID: 1	Date: 24/04/2026	Probability: 60%	Impact: 2

| Description | Inaccurate SQL query generation for complex user inputs, leading to wrong data retrieval. |
| --- | --- |
| Refinement & Context | Sub condition 1: Complex JOINs or nested queries confuse the model. Sub condition 2: The model hallucinates column names or tables. Sub condition 3: Logical operations (AND/OR) are misinterpreted. |
| Mitigation & Monitoring Strategies | 1. Implement few-shot prompting with complex examples. 2. Use a self-correction mechanism where the model reviews its own SQL. 3. Validate the generated SQL syntax against the schema before execution. 4. Use a more powerful language model for complex tasks. |
| Contingency Plan and Management | 1. Alert the user that the query is too complex. 2. Ask the user to break down the query. 3. Display a partial result and ask for confirmation. |
| Trigger | Execution failure of generated SQL or user reporting incorrect results. |
| Status | Mitigation actions in progress |
| Assigned To | AI/ML Engineer |
| Originator | Quality Assurance Team |

## Risk Information Sheet (RIS) for 50% Risk

Risk ID: 3	Date: 24/04/2026	Probability: 50%	Impact: 3

| Description | High latency in generating SQL affecting user experience. |
| --- | --- |
| Refinement & Context | Sub condition 1: API calls to the LLM are inherently slow. Sub condition 2: Large schema metadata increases prompt size and processing time. Sub condition 3: Network latency issues. |
| Mitigation & Monitoring Strategies | 1. Cache common natural language queries and their SQL counterparts. 2. Optimize prompt size by sending only relevant schema parts. 3. Stream the LLM response to provide immediate feedback. 4. Upgrade server infrastructure. |
| Contingency Plan and Management | 1. Show a progress indicator to the user. 2. Disable complex features temporarily. 3. Use a smaller, faster local model as a fallback. |
| Trigger | Average query response time exceeds acceptable threshold (e.g., 5 seconds). |
| Status | Monitoring performance |
| Assigned To | Backend Developer |
| Originator | Performance Team |

## Risk Information Sheet (RIS) for 40% Risk

Risk ID: 2	Date: 24/04/2026	Probability: 40%	Impact: 1

| Description | System vulnerabilities like prompt injection causing unauthorized DB access. |
| --- | --- |
| Refinement & Context | Sub condition 1: Malicious user inputs attempt to alter the prompt instructions. Sub condition 2: Generated SQL includes destructive commands (DROP, DELETE). Sub condition 3: The database user has overly permissive rights. |
| Mitigation & Monitoring Strategies | 1. Apply strict input sanitization and validation. 2. Implement read-only database access for the NL2SQL agent. 3. Use parameterized queries if applicable. 4. Inspect generated SQL for unauthorized operations before execution. |
| Contingency Plan and Management | 1. Block suspicious IP addresses. 2. Revoke database credentials immediately. 3. Restore data from backup if compromised. |
| Trigger | Detection of unauthorized DDL/DML commands in the generated SQL. |
| Status | Implemented |
| Assigned To | Security Engineer |
| Originator | Security Team |

## Risk Information Sheet (RIS) for 30% Risk

Risk ID: 5	Date: 24/04/2026	Probability: 30%	Impact: 2

| Description | Database schema changes breaking the NL2SQL mapping. |
| --- | --- |
| Refinement & Context | Sub condition 1: Developers rename tables or columns without updating metadata. Sub condition 2: New tables are added but not described to the model. Sub condition 3: Data types change, causing SQL execution errors. |
| Mitigation & Monitoring Strategies | 1. Implement a CI/CD pipeline step to automatically synchronize schema metadata. 2. Version control schema changes and map them to NL2SQL prompts. 3. Add regression tests to verify core queries after schema updates. 4. Provide an interface for developers to update table descriptions. |
| Contingency Plan and Management | 1. Revert schema changes if critical. 2. Temporarily disable affected tables from natural language queries. 3. Manually patch the NL2SQL prompt mapping. |
| Trigger | Increase in "Column not found" or similar SQL execution errors after a deployment. |
| Status | Planned |
| Assigned To | Database Administrator |
| Originator | DevOps Team |